## Region 8
WSP USA, INC. | [6 empty] | Inspection Schedule for week of: |  | 2025-11-30 | 2025-12-06
NYSDOT 2025 Region 8 Bridge Inspection | [8 empty] | (Sunday) | (Saturday)
Contract No. D037877 |  |  |  |  | Inspection Teams: | WSP USA: Tom Barrell, Team Leader; Nick Diflorio, ATL |  | 518-330-8841
[6 empty] | WSP USA: Ben Kolesnik, Team Leader; Frank Fraser, ATL |  | 845-596-7106
Salvatore Iodice, Project Manager | [5 empty] | WSP USA: Oleg Shyputa, Team Leader; Dan Rivie, ATL |  | 646-387-3354
Cell PH (917) 763-2519 | [5 empty] | WSP USA: Matt Bacon, Team Leader; Nick Mendola, ATL |  | 774-239-9739
[6 empty] | WSP USA: Kevin Milligan, Team Leader; Christian Flores, ATL |  | 212-784-0037
Amy Hutcheson, Asst. Project Manager | [5 empty] | WSP USA: Dan Hadden, Team Leader; Dionis Demukaj, ATL |  | 845-661-6525
Office PH (914) 449-9038 |  | Cell 917-902-0186 |  |  |  | South Col: Shuangbi Chen, Team Leader; Bo Lun Yang, ATL |  | 518-955-1990
[6 empty] | Lu Eng: Laura Fulford, Team Leader; Ruzen Shafir, ATL |  | 518-577-7117
Karen Tomapat, Scheduling/Office Assistant
Office PH (914) 449-9144 |  | Cell 845-283-0224
Stephanie Santiago, Office Assistant
Cell PH 917-509-0650
Stacie Diamond, Asst. Project Manager
Office PH (914) 449-9136 |  | Cell 845-642-7036 |  |  |  | Access Key: | W = Walking
SL = Step Ladder
Robert Seeley, Quality Control | [6 empty] | EL = Extension Ladder
Cell PH (914) 262-2766 | [6 empty] | BT = Bucket Truck
UB = Under Bridge Unit
TEAM | SCHEDULED DATE | DUE DATE | REGION | COUNTY | BIN | FEATURE CARRIED | FEATURE CROSSED | ACCESS | TOWN/LOC | LANE CLOSED
Chen | 2025-11-10 | 2025-12-16 | 8 | Ulster | 3347440 | CAPE AVENUE | BEER KILL | W, EL | V. Ellenville | N
Chen | 2025-11-10 | 2025-11-29 | 8 | Ulster | 1095450 | 209 209 86031052 | FANTINE KILL | W, EL | V. Ellenville | N