## Chen
Cty | BIN | Carried | Crossed | GTMS | Prev Insp Date | Due Date | Open Flags | PL | GR | Span Count | Prev Field Time (hrs) | Prev Total Time (hrs) | Prev WZTC Time (hrs) | RR Time (hrs) | Access | Booked Access | Remarks | 2024 Team | TOWN
Feb/March
5 | 3345850 | ROSMAN ROAD | MINISCEONGO CREEK | Steel MG | 2023-03-06 | 0306 |  |  | 5 |  | 4 | 12 |  |  | EL, W |  |  | Chen | T. Haverstraw
7 | 3348600 | PONDFIELD ROAD W. | BRONX RIVER | Conc Arch | 2023-03-06 | 0306 |  |  | 4 |  | 3 | 10 |  |  | W |  |  | Chen | V. Bronxville
5 | 3364740 | BLAUVELT ROAD | NAURAUSHAUN BROOK | Conc Culv | 2023-03-08 | 0308 |  |  | 5 |  | 3 | 8 |  |  | W |  |  | Chen | T. Orangetown
7 | 2256050 | PARKWAY ROAD | BRONX RIVER | Steel MG | 2023-03-08 | 0308 |  |  | 4 |  | 8 | 20 |  |  | EL, W |  |  | Chen | V. Bronxville
7 | 2225140 | WAVERLY AVENUE | SHELDRAKE RIVER | Steel MG | 2024-03-12 | 0312 |  | 5 | 3 |  | 2.5 | 14 |  |  | W |  | Under replacement 2024 | Chen | V. Mamaroneck
5 | 3346130 | COUNTY ROAD 93 | NSRR | Steel MG | 2023-03-15 | 0315 |  |  | 5 |  | 2 | 10 |  |  | EL, W |  | Active NSRR tracks | Chen | T. Rampapo
7 | 1037570 | 127 127 87011038 | 907W907W 87025001 | Conc Arch | 2023-03-15 | 0315 |  |  | 5 |  | 3 | 10 |  |  | W |  |  | Chen | T. Harrison
7 | 2262280 | HICKORY GROVE DRV | SHELDRAKE RIVER | Steel MG | 2023-03-15 | 0315 |  |  | 4 |  | 3 | 11 |  |  | W |  |  | Chen | T. Mamaroneck
5 | 3224140 | CHRISTMAS HILL RD | Abandoned MNRR PV LINE | Steel MG | 2023-03-16 | 0316 |  |  | 5 |  | 7 | 20 |  |  | W, EL |  |  | Chen | T. Ramapo
7 | 5523399 | MAMARONECK AVE | MAMARONECK RIVER | Conc Slab | 2023-03-16 | 0316 |  |  | 5 |  | 2 | 10 |  |  | W |  | The culvert can be accessed from the pathway near the left end of the bridge | Chen | C. White Plains
7 | 3358489 | ANDERSON HILL RD | MAMARONECK RIVER | Conc Culvert | 2023-03-16 | 0316 |  |  | 5 |  | 3 | 8 |  |  | W, EL |  |  | Chen | V. Harrison
7 | 2262350 | OLD SAWMILL R.RD | SAWMILL RIVER | Masonry Arch | 2023-03-17 | 0317 |  |  | 5 |  | 2 | 8 |  |  | SL, W |  |  | Chen | T. Greenburgh
7 | 2265700 | SLEEPY HOLLOW RD | TRIS ROCKFELER BR | Conc Frame | 2023-03-17 | 0317 |  |  | 5 |  | 2 | 8 |  |  | W |  |  | Chen | V. Tarrytown
7 | 5523439 | RAMP TO HRP NB | MAMARONECK RIVER | Steel MG | 2024-03-25 | 0325 | 8B2427W007 |  | 5 |  | 3 | 10 |  |  | W |  | NS | Chen | C. White Plains
7 | 2254800 | ELM STREET | SAW MILL RIVER | Steel MG | 2024-03-27 | 0327 | 8B24ASW001 |  | 4 |  | 2 | 12 |  |  | W |  |  | Chen | C. Yonkers
7 | 2225110 | WARD AVENUE | MAMARONECK RIVER | Conc Arch | 2023-03-29 | 0329 |  |  | 4 |  | 2 | 7 |  |  | EL, W |  |  | Chen | V. Mamaroneck
7 | 2254870 | LAKE AVE | SAW MILL RIVER | Steel MG | 2023-03-29 | 0329 |  |  | 5 |  | 4 | 10 |  |  | EL, W |  |  | Chen | C. Yonkers
7 | 1036080 | EB287TOEB100&119 | 119 119 87011043 | P/S Conc Bm | 2023-04-10 | 0410 |  |  | 6 |  | 4 | 9 | 3 |  | BT, WZTC | 2025-03-13 | 30' bucket truck were used for this inspection. An eastbound left lane closure and a westbound left lane closure on Route 100 were also utilized for access to Pier 1. | Chen | T. Greenburgh
7 | 3348230 | OLD POST ROAD | PLAYLAND PARKWAY | Steel MG | 2023-04-11 | 0411 |  |  | 5 |  | 4 | 12 | 3 |  | BT, WZTC | 2025-03-12 |  | Chen | C. Rye
2 | 1070120 | 983W 983W82011001 | 44 44 82022005 | Steel MG | 2023-03-29 | 0329 |  |  | 5 |  | 3 | 10 | 3 |  | BT, WZTC, W | 2025-02-19 |  | Hadden | T. Poughkeepsie
7 | 3348490 | LINCOLN AVENUE | BLIND BROOK | Steel MG | 2023-03-06 | 0306 |  |  | 5 |  | 2 | 12 |  |  | W, SL |  |  | Chen | T. Rye
7 | 7000110 | MNRR NH LINE | 1 1 87035012 | Steel Truss | 2023-02-26 | 0226 |  |  | 5 |  | 2 | 6 |  |  | W |  | GBSI | Chen | V. Port Chester
April
7 | 3358640 | SAXON PARK ENTRCE | MAMARONECK RIVER | Steel MG | 2023-04-04 | 0404 |  | 14 | 5 |  | 2 | 8 |  |  | W,SL |  |  | Chen | T. Mamaroneck
7 | 3348180 | ARMONK RD CONNECT | BROADWAY CR29A | Conc Frame | 2023-04-12 | 0412 |  |  | 5 |  | 2 | 10 |  |  | W |  |  | Chen | T. North Castle
7 | 2225100 | STATION PLAZA | MAMARONECK RIVER | P/S Conc BB | 2023-04-18 | 0418 |  | 5 | 5 |  | 4 | 14 |  |  | EL, W |  | 2020: Further investigation is recommended to investigate the 5 Ton posting. | Chen | V. Mamaroneck
7 | 3348690 | 119 119 87012005 | 907G BRP | Conc Frame | 2023-04-24 | 0424 |  |  | 5 |  | 2 | 10 |  |  | W |  |  | Chen | C. White Plains
7 | 1037130 | 116 116 87011072 | TITICUS RIVER |  | 2023-04-19 | 0419 |  |  | 4 |  | 3 | 9 |  |  | W |  |  | Chen | T. North Salem
7 | 3347960 | LEXINGTON AVENUE | KISCO RIVER | Conc Slab | 2023-04-20 | 0420 |  |  | 5 |  | 2 | 8 |  |  | W |  | DEP | Chen | V. Mt. Kisco
7 | 3348420 | GALLOWS HILL ROAD | PKSKL HOLLOW CRK | Steel MG | 2023-04-24 | 0424 |  |  | 5 |  | 7 | 21 | 6 |  | UB60, WZTC | 2025-04-04 |  | Chen | T. Cortlandt
7 | 5521680 | EHPA DPW ROAD | HUTCHINSON RIVER | Steel Culv | 2023-04-24 | 0424 |  |  | 7 |  | 2 | 1.5 |  |  | W |  |  | Chen | C. New Rochelle
7 | 2265880 | WATCH HILL ROAD | TRIB.FURNACE BRK | Steel Culv | 2023-04-26 | 0426 |  |  | 5 |  | 2 | 8 |  |  | W |  |  | Chen | T. Cortlandt
7 | 2265140 | FENIMORE ROAD | SHELDRAKE RIVER | Conc Frame | 2023-04-27 | 0427 |  |  | 5 |  | 1.5 | 8 |  |  | SL, W |  |  | Chen | V. Mamaroneck
7 | 2225270 | ORCHARD AVENUE | BLIND BROOK | Steel MG | 2024-04-10 | 0410 |  | 14 | 5 |  | 2.5 | 12 |  |  | W |  |  | Chen | C. Rye
7 | 2265790 | SOUTH BARRY AVE | OTTER CR.TIDAL B. | Steel MG | 2024-04-17 | 0417 | 8B241ZW014 |  | 4 |  | 5 | 12 |  |  | SL, W |  | inspect at low tide | Chen | V. Mamaroneck
7 | 2265490 | STATION ACCESS RD | PALMER AVENUE | Steel MG | 2023-04-28 | 0428 |  |  | 4 |  | 3 | 12 | 3 |  | WZTC, EL | 2025-04-17 | SILO in 2020, do with 2265509 | Chen | V. Bronxville
7 | 2265509 | BRNXVILLE STA.ACC | PALMER AVENUE | Steel MG | 2023-04-28 | 0428 |  |  | 4 |  | 3 | 12 | 3 |  | WZTC, EL | 2025-04-17 | SILO in 2020, do with 2265490 | Chen | V. Bronxville
7 | 5502220 | 987GX | 129 129 87011061 | Steel MG | 2024-05-06 | 0506 | 8B24XUW004 & 005 |  | 4 |  | 8 | 24 | 8 |  | BT, WZTC, EL, W | 2025-04-24 | SILO in 2023 Electrical power line under pier 1, use extra caution | Chen | T. Yorktown
May
7 | 1000121 | 1 1 87035019 | BYRAM RIVER | Conc T-Beam | 2024-05-01 | 0501 | 8B24ASW003, 004 & 005 |  | 4 |  | 5 | 30 |  |  | W, EL |  | SILO in 2021 | Chen | V. Port Chester
2 | 1027139 | 55 55 82032023 | WAPPINGER CREEK | P/S Conc BB | 2023-05-08 | 0508 |  |  | 6 |  | 5 | 8 | 4 |  | UB60, WZTC | 2025-05-02 |  | Chen | T. Poughkeepsie
7 | 5524380 | 907W 907W87025029 | BLIND BROOK | Frame | 2023-05-08 | 0508 |  |  | 6 |  | 2 | 8 |  |  | W |  |  | Chen | V. Rye Brook
7 | 2265840 | ACCESS RD PKG LOT | BRONX RIVER | Steel MG | 2024-05-09 | 0509 | 8B240TW006 | 16 | 4 |  | 5 | 20 |  |  | EL, W |  |  | Chen | T. Greenburgh
7 | 1016590 | 22 22 87034159 | STONE HILL RIVER | Conc T-Beam | 2024-05-14 | 0514 |  | 28 | 5 |  | 3 | 8 |  |  | W |  |  | Chen | T. Bedford
7 | 2265830 | HARLAN DRIVE | CARPENTER CREEK | Steel Culv | 2024-05-14 | 0514 |  | 15 | 5 |  | 2 | 8 |  |  | W |  |  | Chen | C. New Rochelle
2 | 1052390 | HOLMES ROAD | 84I 84I82021177 | Steel MG | 2023-05-16 | 0516 |  |  | 5 |  | 8 | 16 | 5 |  | BT, WZTC | 2025-05-07 |  | Chen | T. East Fishkill
7 | 1077340 | 9A 9A87488A01 | 9A 9A87032119 | Steel MG | 2023-05-16 | 0516 |  | 25 | 6 |  | 2 | 8 |  |  | EL, W |  |  | Chen | T. Mt. Pleasant
7 | 2262300 | FENIMORE ROAD | WINDING BROOK | Steel MG | 2023-05-16 | 0516 |  |  | 6 |  | 2 | 7 |  |  | W |  |  | Chen | T. Mamaroneck
7 | 3348670 | 907GX | BRONX RIVER | Conc Arch | 2023-05-16 | 0516 |  |  | 5 |  | 2 | 6 |  |  | W |  |  | Chen | T. Greenburgh
7 | 1005020 | WARREN RD | 9 | Steel MG | 2023-05-19 | 0519 |  |  | 5 |  | 7 | 26 | 6 |  | BT, WZTC | 2025-05-13 |  | Chen | V. Croton on Hudson
7 | 3348630 | 907GX | BRONX RIVER | P/S Conc Slab | 2023-05-19 | 0519 |  |  | 6 |  | 3 | 8 |  |  | W |  |  | Chen | T. Greenburgh
2 | 1032560 | SHENANDOAH ROAD | 84I 84I82021111 | Steel MG | 2023-05-31 | 0531 |  |  | 5 |  | 8 | 16 | 7 |  | BT, WZTC | 2025-05-20 | Walking, Extension Ladder (Spans 1 & 5), Bucket Truck (Spans 2-4) w/ Lane Closure & Shadow Vehicle on I-84. | Chen | T. East Fishkill
5 | 3370090 | JB CLARKRAILTRAIL | 303 303 85011019 | Steel Truss | 2023-06-02 | 0602 |  |  | 6 |  | 5 | 7 | 3 |  | BT, WZTC | 2025-05-30 |  | Chen | T. Orangetown
7 | 7036130 | EX-NYCRR PUTNAM B | 100 100 87014143 | Steel GFB | 2023-04-14 | 0414 |  |  | 5 |  | 2 | 6 |  |  | W |  | GSBI | Chen | T. New Castle
June
7 | 1050450 | COUNTY ROAD 306 | PEEKSKILL HOL CRK | P/S Conc BB | 2023-06-06 | 0606 |  |  | 6 |  | 2 | 8 |  |  | W |  |  | Chen | C. Peekskill
7 | 2262360 | BROOKSIDE WAY | BLIND BROOK | Slab | 2023-06-06 | 0606 |  |  | 5 |  | 2 | 10 |  |  | W |  |  | Chen | V. Rye Brook
7 | 3358610 | ANDERSON HILL RD | BLIND BROOK | Slab | 2023-06-08 | 0608 |  |  | 5 |  | 3 | 8 |  |  | W, EL |  |  | Chen | V. Harrison
7 | 5500562 | 987D987D87011029 | LOCKWOOD AVENUE | P/S Conc MG | 2024-06-11 | 0611 | 8B2427W012 & 013 |  | 4 |  | 4 | 14 | 4 |  | BT, WZTC, SL, W | 2025-06-06 |  | Chen | C. Yonkers
7 | 3358510 | MANURSING ISL RD | PLAYLAND LAKE | P/S Conc BB | 2023-06-13 | 0613 |  |  | 6 |  | 3 | 10 |  |  | W |  |  | Chen | C. Rye
3 | 1003300 | 208 208 83011059 | 17 17 83101221 | Steel MG | 2023-06-15 | 0615 |  |  | 5 |  | 6 | 20 | 5 |  | BT, WZTC | 2025-06-13 |  | Chen | T. Monroe
7 | 2265710 | KYKUIT HILL RD | LAKE ROAD | Conc Frame | 2023-06-15 | 0615 |  |  | 5 |  | 1.5 | 4 |  |  | SL, W |  | Access to the top of bridge is through Kykuit gate (owned by the Green Rock Corporation at 200 Lake Road, Telephone #914-631-4581). | Chen | T. Mt. Pleasant
7 | 3348510 | WESTERLEIGH ROAD | BLIND BROOK | P/S Conc BB | 2023-06-19 | 0619 |  |  | 5 |  | 2 | 8 |  |  | W |  |  | Chen | T. Harrison
3 | 1052520 | MC MANUS ROAD | 84I 84I83011174 | Steel MG | 2023-06-22 | 0622 |  |  | 5 |  | 5 | 12 | 5 |  | BT, WZTC | 2025-06-27 | WZTC needed in 2025 when Fatigue Life expires | Chen | T. Wawayanda
7 | 1070500 | HOSPITAL RD | 987F | Steel Mb/Girder | 2023-06-22 | 0622 |  |  | 5 |  | 4 | 14 |  |  | EL |  |  | Chen | T. Mt. Pleasant
2 | 3343560 | HURLEY ROAD | WAPPINGER CREEK | Steel MG | 2023-06-22 | 0622 |  |  | 4 |  | 5 | 10 |  |  | Rowboat, EL, SL, W |  |  | Chen | T. Pleasant Valley
7 | 1036140 | 100 100 87014161 | NEW CROTON RESVOR | Steel MG | 2023-06-23 | 0623 |  |  | 5 |  | 6 | 20 | 4.5 | 0 | UB60, WZTC, Skiff | 2025-06-16 | DEP 2019 Access: Walking, UBIU 60', Lane Closure, Shadow Vehicle, Skiff. UBIU needed on both sides of the bridge. | Chen | T. Yorktown
2 | 1005329 | 9 82052020 | FALLKILL CREEK | Steel MG | 2023-06-27 | 0627 |  |  | 5 |  | 4 | 10 | 3 |  | UB40, WZTC in 2029 |  | In 2019, Fatigue life analysis was performed for cover plate weld in this inspection. Hand-on for Special Emphasis details was waived therefore; UBIU and WZTC are not needed until next 100% hands-on visual inspection due in 2029. | Chen | C. Poughkeepsie
7 | 5053371 | 987F987F87012049 | 119 119 87011030 | Steel MG | 2023-06-27 | 0627 |  |  | 7 |  | 3 | 8 | 3 |  | UB60, WZTC | 2025-06-24 |  | Chen | V. Elmsford
7 | 5053372 | 987F987F87012049 | 119 119 87011030 | Steel MG | 2023-06-27 | 0627 |  |  | 7 |  | 3 | 8 | 3 |  | UB60, WZTC | 2025-06-24 |  | Chen | V. Elmsford
7 | 5500659 | 987DX | SAW MILL RIVER | P/S Conc BB | 2023-06-27 | 0627 |  |  | 4 |  | 2 | 12 |  |  | W |  |  | Chen | V. Hastings on Hudson
7 | 5500969 | 987DX | KISCO AVENUE | Steel MG | 2023-07-05 | 0705 |  |  | 5 |  | 4 | 10 | 3 |  | 75' ML, WZTC | 2025-06-23 |  | Chen | V. Mt. Kisco
July
2 | 1006410 | 9GX | Hudson Valley Rail Trail | Conc Frame | 2023-07-06 | 0706 |  |  | 6 |  | 3 | 8 |  |  | W |  |  | Chen | C. Poughkeepsie
2 | 1005279 | 9 9 82052012 | PINE STREET | Steel MG | 2023-07-18 | 0718 |  |  | 5 |  | 3 | 10 | 2 |  | BT,EL,W |  |  | Chen | C. Poughkeepsie
2 | 3343250 | TODD HILL ROAD | SPROUT CREEK | Box Beam or Box Girders - Multiple | 2023-07-19 | 0719 |  |  | 5 |  | 2 | 6 |  |  | W |  |  | Chen | T. Lagrange
3 | 1014550 | 17M 17M83011018 | MNRR PJ LINE | Conc Frame | 2023-07-20 | 0720 |  |  | 4 |  | 2 | 12 |  | 2 | RR Flagger, EL, W | 2025-07-23 |  | Chen | T. Wallkill
4 | 1080050 | PUDDING ST | 987G | Steel MG | 2023-07-20 | 0720 |  |  | 7 |  | 3 | 10 | 3 |  | BT, WZTC | 2025-07-08 |  | Chen | T. Putnam Valley
2 | 3343260 | COUNTY ROAD 21 | SPROUT CREEK | Steel MG | 2023-07-20 | 0720 |  |  | 6 |  | 2 | 7 |  |  | EL,W |  |  | Chen | T. Lagrange
3 | 3344900 | NEW VERNON ROAD | MNRR PJ LINE | Steel MG | 2024-07-11 | 0711 | 8B24VLW021, 022 & 023 |  | 4 |  | 9 | 30 | 8 | 8 | UB60, WZTC, W, RR Flagger | 2025-07-18 | NS SE exemption?, UB60 deploy off both sides | Chen | T. Mt. Hope
3 | 1052570 | GOSHEN TURNPIKE | MNRR PJ LINE & 84I 84I83011208 | Steel MG | 2024-07-17 | 0717 | 8B240TW014, 015 & 016 |  | 4 |  | 10 | 35 | 6 | 4 | UB60, WZTC, W, RR Flagger | 2025-07-17 | SILO in 2023 no RR flagger needed (tracks removed) | Chen | T. Wallkill
4 | 1052741 | 84I 84184031004 | LUDNGTNVL RD-CR43 | Steel MG | 2024-07-24 | 0724 | 8B245VW009 |  | 4 |  | 7 | 14 | 6 |  | BT, WZTC, EL, W | 2025-07-16 | Try to inspect with sister in 2026 | Chen | T. Kent
2 | 1006360 | 9D 9D82033001 | 84I 84I82021014 | Steel MG | 2024-08-08 | 0808 | 8B24XUW017 & 018 |  | 4 |  | 8 | 28 | 6 |  | BT, WZTC, EL, W | 2025-07-22 | NS NBI Subs = 3 Call Newburgh Beacon Bridge Office – (845) 831-3700 | Chen | T. Fishkill
4 | 2223870 | MOONEY HILL ROAD | MNRR BE LINE | Steel MG | 2024-07-11 | 0711 | 8B24XUW015 |  | 4 |  | 5 | 15 |  |  | EL, W Notify MNRR |  | RR flagging time 3 hrs. | Chen | T. Patterson
2 | 2343470 | C.COLEMAN BLVD | SWAMP RIVER | Steel MG | 2023-06-28 | 0628 |  |  | 5 |  | 3 | 8 |  |  | W |  | A pedestrian bridge is present within 5’ of the left side of the bridge. | Chen | V. Pawling
5 | 2269890 | TWIN ELMS LANE | TRIBUTARY TO HACKENSACK RIVER | Conc Culvert | 2023-08-08 | 0808 |  |  | 6 |  | 2 | 8 |  |  | W |  |  | Chen | T. Clarkstown
August
3 | 1045080 | 293 293 83011029 | MINE LAKE INLET | Conc Arch | 2023-08-10 | 0810 |  |  | 5 |  | 2 | 8 |  |  | Rowboat | 2025-08-01 |  | Chen | T. Highlands
3 | 1091250 | GREENVILLE TPKE | 84I 84I83011066 | Steel MG | 2023-08-16 | 0816 |  |  | 5 |  | 7 | 20 | 6 |  | BT, WZTC | 2025-08-05 | SILO in 2020 | Chen | T. Greenville
3 | 1040520 | COUNTY ROAD 105 | TRIB RAMAPO RIVER | Conc (cont) Culv | 2023-08-22 | 0822 |  |  | 5 |  | 3 | 8 |  |  | W | 2025-08-06 |  | Chen | T. Monroe
3 | 1040959 | 211 211 83013009 | MASONIC CREEK | Conc Culv | 2023-08-14 | 0814 |  |  | 5 |  | 2 | 8 |  |  | W | 2025-08-06 |  | Chen | T. Wallkill
2 | 1032360 | 82 82 82011247 | E B WAPPINGER CRK | [12 empty] | 2025-08-07
2 | 5502410 | 987G987G82031143 | JAMES BAIRD PARK ENTRANCE ROAD | [12 empty] | 2025-08-07
6 | 3347710 | TANNERY BROOK RD | SAW KILL | Steel MG | 2023-08-22 | 0822 |  |  | 4 |  | 7 | 16 |  |  | W, EL | 2025-08-11 | HVA REQUEST MANDATORY 2025 | Chen | T. Woodstock
3 | 1068780 | ANTHONY WAYNE DR | 987C 987C83021004 | Conc Frame | 2023-08-08 | 0808 |  |  | 5 |  | 1.5 | 10 |  |  | W | 2025-08-13 |  | Chen | T. Woodbury
3 | 1022230 | 32 83011050 | WOODBURY CR TRIB | Conc Culv | 2023-08-30 | 0830 |  |  | 5 |  | 3 | 10 |  |  | W | 2025-08-13 |  | Chen | T. Woodbury
6 | 1041090 | 212 212 86011114 | TANNERY BROOK | Conc Slab | 2023-08-22 | 0822 |  |  | 4 |  | 2 | 8 |  |  | W | 2025-08-12 |  | Chen | T. Woodstock
6 | 1041010 | 212 212 86011041 | BEAVER KILL | Box Beam or Box Girders - Multiple | 2023-08-28 | 0828 |  |  | 5 |  | 3 | 10 |  |  | W, EL | 2025-08-12 |  | Chen | T. Woodstock
6 | 1007370 | 9W 9W86033097 | ESOPUS CREEK | Steel Truss | 2024-08-27 | 0827 | 8B24T1W019 |  | 4 |  | 16 | 40 | 4 |  | Bucket Boat, BT, WZTC | 8/18 & 8/19 | NS | Chen | T. Saugerties
2 | 3342980 | DOGTAIL CORNERS RD | TENMILE RIVER | [12 empty] | 2025-08-21
6 | 1007370 | 9W 9W86033097 | ESOPUS CREEK | Steel Truss | 2024-08-27 | 0827 | 8B24T1W019 |  | 4 |  | 16 | 40 | 4 |  | Bucket Boat, W | 2025-08-25 | NS | Chen | T. Saugerties
3 | 3344900 | NEW VERNON ROAD | MNRR PJ LINE | Steel MG | 2024-07-11 | 0711 | 8B24VLW021, 022 & 023 |  | 4 |  | 9 | 30 | 8 | 8 | Flagger, W | 2025-08-27 |  | Chen | T. Mt. Hope
3 | 1040980 | 211 211 83013083 | WALLKILL RIVER |  | 2023-09-12 | 0912 |  |  | 7 |  | 4 | 7 | 3 |  | UB40, WZTC | 2025-08-28 | Crew + F | Chen | T. Montgomery
3 | 1026740 | 52 52 83031103 | TIN BROOK | Conc Slab | 2023-08-17 | 0817 |  |  | 5 |  | 3 | 8 |  |  | W | 2025-08-28 |  | Chen | T. Montgomery
223
3 | 1022240 | 32 83011099 | MOODNA CREEK | Steel Truss | 2023-09-06 | 0906 |  |  | 5 |  | 7 | 20 | 6 |  | UB60, BT, WZTC |  |  | Chen | V. Cornwall
7 | 3349020 | 907GX | MNRR HA LINE | [12 empty] | out
Formulas:
Booked Access = +[Booked Access, row above]